## Slide 1
NASA Lessons
From Columbia
Wayne Hale
Director of Human Spaceflight
Notice: Information Subject to Export Control Laws.
This document contains NO “Technical Data” as defined under
The International Traffic in Arms Regulations (ITAR) (22 C. F. R. 120.10) .
DTC Case TA 2777-09.

## Slide 2: Evil Bad Guys Cause Accidents?
Most accidents originate in actions committed by reasonable, rational individuals who were acting to achieve an assigned task in what they perceived to be a responsible and professional manner.
— Peter Harle, Director of Accident Prevention,Transportation Safety Board of Canada and former RCAF pilot, 'Investigation of human factors: The link to accident prevention.' In Johnston, N., McDonald, N., & Fuller, R. (Eds.), Aviation Psychology in Practice, 1994

## Slide 3
Success teaches us nothing;
only failure teaches
Admiral Hyman G. Rickover
Father of the US Nuclear Navy

## Slide 4: Success and Adversity
87 successful space shuttle flights between Challenger and Columbia
“Cultural traits and organizational practices detrimental to safety were allowed to develop including reliance on past successes as a substitute for sound engineering practices …‟
  - Columbia Accident Investigation Board, September 2003
Several Technical Issues faced by the Space Shuttle Program before Columbia:
Ball-Strut-Tie Rod Assembly (BSTRA) Main Prop System Flowliner Cracks
TVC Hydraulic Power Unit ET Foam loss
ETA Ring Structural Margin SRB Nozzle Pocketing
SRB Insulation Ply Lifting SRB Nozzle Bonds
SRB Propellant Cracks Payload Bay Door Power Drive Unit
MLP Corrosion – Hydrogen Vent Line Orbiter Corrosion Rudder/Speedbrake
Orbiter Wiring Transporter Bearings
Pyrotechnic Duds Main EngineTurbine Tip Seals

## Slide 5: Minor Maintenance Issue – Tile Damage

## Slide 6: As Columbia Counted Down to Launch
The Space Shuttle perceived as “Operational” and “a Mature System” after flying for 22 years and 112 flights
  No major surprises expected
  Environments and hardware thought to be well understood.
NASA under intense budgetary pressure – costs must be reduced
  Annual inflation adjusted Shuttle budget reduced 45% between 1991 and 2002
NASA under intense schedule pressure – Space Station Assembly significantly behind schedule
Columbia mission STS-107 was considered “routine” and “low complexity”
On Orbit repair to heat shield considered impossible “Nothing We Can Do” – an “Accepted Risk”

## Slide 7: Success leads to Failure
Success can be more dangerous than failure
Learn to ask for help early
Keep your leaders informed
Don’t be like the frog in the pot of water – boiled to death slowly
Encourage your subordinates to report problems and ask for help
  Don’t punish them inadvertently – encourage ‘bad news’ reports
  Don’t punish them by over helping them
Failure really is an option – Lucy V. Kranz

## Slide 8: NASA’s Return to Flight Rationale
I
Elimination of Critical Debris
II
Impact Detection During Ascent
III
On-Orbit Debris Impact/Damage Detection
IV
On-Orbit TPS Repair
(Tile & RCC)
V
Crew Rescue
Primary
Hazard
Control
Warning
Devices
Special
Procedures
5
6
7
8
9

## Slide 9: Space Shuttle Risk of Loss Vehicle and Crew
STS-107
TPS
All other Risk
Elimination of Ascent Debris
On-Orbit Inspection and Repair
Contingency Shuttle Crew Survival Capability
20%
80%

## Slide 10: Space Shuttle Risk of Loss Vehicle and Crew
STS-107
TPS
All other Risk
Enhanced Systems Engineering and Integration
Enhanced Safety, Mission Assurance, and Independent Oversight
Post- RTF
Residual
Risk
Cultural Change
Fixes for Aging Orbiter Issues Identified

## Slide 11: Post Columbia
Several Senior (retired) NASA officials involved in Space Shuttle Development gave us two areas to avoid:
  On Orbit Tile Repair will never work – we tried everything 20 years ago and nothing worked
  Do not change the outer mold line of the shuttle stack – the aerodynamics are too hard to get right
In Return to Flight we were forced to do both
  On Orbit Tile and RCC repair materials and techniques developed and validated
  Ice-Frost-Ramp reduced, Protuberance-Air-Load ramp removed, wind tunnel campaign verified aero loads

## Slide 12: Addressing the Culture
NASA Administrator Sean O’Keefe emphatically instructed all employees to “Accept the [CAIB] Report”
  Posters all over the agency asked “Have you read the report?”
Independent Review Teams (ASAP, RTFTG, others) met almost continuously to ensure the Space Shuttle Program rigorously completed all requirements for return to flight
Program Management power curbed with checks and balances from Independent Technical Authorities
Behavior Sciences Technology company hired to retrain NASA managers

## Slide 13: Safety and Management Changes
Mission Management Team (MMT)
  Significant changes to the composition and focus of the MMT
  Formal training requirements established
  Now a well-functioning real-time management body
  New MMT room designed to facilitate open communication
Safety and Mission Assurance (S&MA)
  Reinvigorated independent S&MA at HQ and Centers
  Strengthened Shuttle Program S&MA and Systems Engineering and Integration capabilities
  Established Independent Technical Authority and technical warrant holders
NASA Engineering and Safety Center
  Established at Langley as an independent
  source of engineering and technical expertise
  Important resource for Space Shuttle engineering

## Slide 14: Management Re-Training
Reading assignments on management culture and best practices
  “Angle of Attack” about Apollo 1 Fire
  “The Challenger Launch Decision”
Hiring of two academic management experts to embed with the mission management team
  Dr. Don Van Ende from Trinity University
  Dr. Chris Jones from University of Central Florida
Multiple MMT training sessions and very specific certification requirements
Lectures by experts on management culture
  Dr. Diane Vaughn
  Dr. Charles Perrow
  Dr. Nancy Levison
  Dr. Edward Tufte

## Slide 15: Culture Change Initiatives
Attendance at MMT and PRCB mandatory for senior managers (substitutes not allowed)
Inclusion of all NASA centers in decision making emphasized
New Mission Management Team room built
  Round Table
  Teleconferenced all meetings with all NASA Centers
  Call on all parties – not just subject matter experts – for their advice and review
Smaller, ‘warmer’ conference rooms designed for MMT
Behavorial Sciences Technology, Inc. Hired to observe and debrief all Space Shuttle Program meetings
  Emphasis on drawing out ‘weak signals’
  Emphasis on non-confrontational management style
  Emphasis on civility and courtesy

## Slide 16: Management Classes Added
Cockpit Resource Management course by Flight Safety International developed into Spaceflight Resource Management class taught internally
Safety Culture Training Class developed
Lessons in writing ‘white papers’ vs. building PowerPoint presentations
Lessons in human social interaction were instituted
  How to draw out dissenting opinions
  The valuable use of silence in meetings

## Slide 17: Fighting the Culture Wars
Many ‘old line’ managers resisted the culture changes as ‘coddling’ the workforce – and wasting time
While some personnel transfers to S&MA were made, it was still regarded as a sideline organization to be avoided
  Cultural Biases are hard to change
Senior NASA HQ management agonized over the slowness of return to flight
  “Take the foam off the bipod and fly in October 2003”
Some independent reviewers remained skeptical – hostile – to the very end
Virtually everyone hated BST

## Slide 18: More Pushback
Frequently heard comment: “The CAIB got it wrong”
  Generally heard from senior (old line) managers
  Generally regarding NASA organizational culture
“Not invented here” syndrome continues to exacerbate inter-center relationship difficulties
Email from a retired senior NASA executive to me in late 2015 (typical of many received):
“The general thrust of the questions give me some concern. The strong emphasis seems to be targeted toward "Organizational Culture". The principal thought appears to be correcting a culture where young engineers at a low organizational level could not exercise proper influence. I am not aware of any organizational cultural flaw of this nature having any effect on the Shuttle Program Management's lack of attention to foam shedding from the tank. What am I missing? The so called organizational cultural flaw attributed to the Challenger accident is a very different issue. The o-ring discussion between a contractor and MSFC that occurred prior to the Challenger launch has no relationship to Columbia that I am aware of. Are we chasing ghosts invented by the CAIB?”

## Slide 19: Embrace Dissent
“If we are all in agreement on the decision – then I propose we postpone further discussion of this matter until our next meeting to give ourselves time to develop disagreement and perhaps gain some understanding of that the decision is all about”
– Charles E. Wilson, CEO of General Motors, 1950
Listen to weak signals and poor arguments for the truth they hold but are having difficulty communicating.
Tip: Appoint a ‘devil’s advocate’ to make the argument on the other side when all appear to be in agreement.

## Slide 20: Afraid to Ask for Help
Sometimes people are afraid to ask for help because they might get more help than they want. Or at least more management attention than they want.
Many times our team members want to be the ‘hero’ that saves the program – the one that works all day and all night and gets the vehicle to flight no matter what
More often than not, those ‘heroes’ are unsuccessful, and the issues come out very late – when resources could have been provided to help solve them earlier
One Project Manager: “Don’t worry Boss, we have it under control. I’ll let you know when to worry.” Me: “That makes me worry more than ever”

## Slide 21: Trying to break out of the mold
Commercial Crew and Commercial Cargo programs are an attempt to lighten NASA control and allow for innovation and flexibility – and lower cost
Shuttle had 40,000 specifications and requirements, Constellation had (estimated) over 100,000 specifications and requirements, Commercial Crew has about 10,000 specifications and requirements
NASA trying to relinquish control in areas where the technology is more mature and private companies can be motivated to adequately provide safety and reliability at lower cost
Results are open, human spaceflight certification is pending.

## Slide 22: http://www.nasa.gov/pdf/469245main_GovernmentInsightForCommercialCrewTransportation.pdf

## Slide 23: Fifteen Years On – What Has Changed
Anecdotal evidence that emphasis on safety has eroded
Alternatively, emphasis on process and ‘safety’ have increased cost and delayed schedule critically on new NASA programs
  Balance is needed
Anecdotal evidence that old management styles have crept back in
  Not looking for dissenting opinions
  More concerned with schedule and cost than risk
Some changes have devolved into ‘checking the square’
  “No dissenting opinions” frequent statement on management briefings

## Slide 24: NASA as a High Reliability Organization
Preoccupied with [the Possibility of] Failure
A Learning Organization
  Internal Lessons Documented, Studied
  Lessons from Others Gleaned and Studied
Reluctant to Simplify Interpretations
Sensitive to Operations
Committed to Resilience
  Redundancy or “defense in depth”
Deferential to Expertise
  Management defers to Engineering defers to “hands-on” personnel

## Slide 25: Ten Enduring Lessons
It can happen to you.
Focus.
Speak up.
You are not nearly as smart as you think you are.
Dissention has tremendous value.
Question the Conventional Wisdom
Do good work.
Engineering is done with numbers
Use your imagination
Nothing worthwhile was accomplished without taking risk.